## Gant_chart
|  |  | Height | 2026-03-19
Activity | Start Date | End Date | Duration | Status | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31
Login Page | 2026-03-01 | 2026-03-05 | 5 | Completed | 2026-03-01: Completed; 2026-03-02: Completed; 2026-03-03: Completed; 2026-03-04: Completed; 2026-03-05: Completed
PLP | 2026-03-03 | 2026-03-17 | 15 | Pending | 2026-03-03: Pending; 2026-03-04: Pending; 2026-03-05: Pending; 2026-03-06: Pending; 2026-03-07: Pending; 2026-03-08: Pending; 2026-03-09: Pending; 2026-03-10: Pending; 2026-03-11: Pending; 2026-03-12: Pending; 2026-03-13: Pending; 2026-03-14: Pending; 2026-03-15: Pending; 2026-03-16: Pending; 2026-03-17: Pending
PDP | 2026-03-05 | 2026-03-07 | 3 | Pending | 2026-03-05: Pending; 2026-03-06: Pending; 2026-03-07: Pending
Cart | 2026-03-07 | 2026-03-14 | 8 | Completed | 2026-03-07: Completed; 2026-03-08: Completed; 2026-03-09: Completed; 2026-03-10: Completed; 2026-03-11: Completed; 2026-03-12: Completed; 2026-03-13: Completed; 2026-03-14: Completed
Payment Page | 2026-03-09 | 2026-03-23 | 15 | Defered | 2026-03-09: Defered; 2026-03-10: Defered; 2026-03-11: Defered; 2026-03-12: Defered; 2026-03-13: Defered; 2026-03-14: Defered; 2026-03-15: Defered; 2026-03-16: Defered; 2026-03-17: Defered; 2026-03-18: Defered; 2026-03-19: Defered; 2026-03-20: Defered; 2026-03-21: Defered; 2026-03-22: Defered; 2026-03-23: Defered
Formulas:
End Date = [Start Date]+[Duration]-1

## pareto
Defect Type | Count | region | % of Total | Cummulative percentage | region | South
Payment gateway error | 40 | North | 32 | 0
Data Validation | 30 | south | 24 | 24
Login Page | 25 | North | 20 | 24
UX issue | 15 | North | 12 | 24
Performance issue | 10 | south | 8 | 32
cart page | 5 | East | 4 | 32

## Sheet2
Defect Type | bug_Count | Total Percentage | cummulative total | cum %
Payment gateway error | 40 | 33.33% | 33.33%
Data Validation | 30 | 25% | 58.33%
Login Page | 25 | 20.83% | 79.17%
UX issue | 15 | 12.5% | 91.67%
Performance issue | 10 | 8.333% | 100%
| 120 | 100%

## Sheet4
Defect Type | Count | Total Percentage | cummulative total
Payment gateway error | 40 | 33.3333 | 33.3333
Data Validation | 30 | 35.2941 | 68.6275
Login Page | 25 | 42.3729 | 111.0003
UX issue | 15 | 40.5405 | 151.5409
Performance issue | 10 | 41.6667 | 193.2075
ds | 5 | 33.3333 | 226.5409
er | 4 | -40 | 186.5409
rrtr | 3 | -246 | -59.4591
rtrt | 2 | 66.6667 | 7.2075
tyt | 1 | 100 | 107.2075
t
tyt
Performance issue
ds
er
rrtr
rtrt
tyt
t
tyt